Proposed Long Lake Integrated/ Adaptive Lake Management Plan

2014-2023

March 3, 2014

Prepared for:

Kitsap County and CILL

Tetra Tech, Inc.

1420 Fifth Ave, Suite 550

Seattle, WA  98101

# Restoration History

Long Lake was studied by personnel from the University of Washington for 20 consecutive years from 1976 to 1995 to evaluate the effectiveness of several restoration techniques (Welch, 1996).  The lake water level was drawn down about 6 feet (1.8 m) during the summer of 1979 to desiccate previously submersed rooted plants and to consolidate the flocculent sediment.  While lake sediment substantially dried in laboratory experiments, they failed to consolidate over the 40% of lake sediments exposed, because seepage water prevented sediment drying.  Although exposed plants desiccated and biomass was low the following year (1980), they began to recover by 1981 and were back to maximum biomass by 1984 (Jacoby et al., 1982). Also a small area in the north end was dredged during the 1979 drawdown to widen and deepen the outlet although this was too localized to affect internal phosphorus (P) loading throughout the lake.

The lake was treated to inactivate sediment P with alum in the fall of 1980 with a dose of 5.5 mg/L Al and again at the same time and concentration in 1991.  In the meantime, rooted plants were mowed with a harvester during the summer of 1988, 1989 and 1990, removing 10, 43 and 69% of the peak plant biomass per year, respectively.

The first alum treatment was highly effective for the first four years and maintained modest water quality improvement on average for the next seven years, compared to pretreatment TP (Figure 1).  The high summer mean TPs of 69 and 78 µg/L, which occurred in 1977 and 1978, did not recur during that eleven-year period, although TP and chlorophyll (chl) were rather high (66 and 36 µg/L, respectively) in 1985, due mostly to a rooted plant-die-off, and in 1990 (55 and 40 µg/L), prior to the second alum treatment (Figure 2). These were the highest chl concentrations during the twenty-year period.  Note that transparency varied in inversely with chl, with the highest transparency occurring with the lowest chl (Figure 2).  Transparency also varied directly with macrophyte biomass (Jacoby et al., 2001).

The second alum treatment was applied in late summer 1991 at 5.5 mg/L Al. The following summer TP averaged only 20 µg/L, the lowest summer mean ever. The summer mean for the four-year post treatment was slightly above 30 µg/L and chl averaged less than 10 µg/L, similar to the four-year mean following the 1980 treatment (Figure 1).

Figure 1. Mean whole-lake summer (June-September) TP, chl and Secchi transparency for groups of study years before and after three alum treatments in Long Lake, Kitsap.  Pre 2006 data from Welch (1996).  Data for 2006 serves as a partial reference for post-alum years 2007-2010.

Monitoring of the lake by UW ceased after 1995, but was resumed in 2006 as part of a long-term project by Kitsap County and CILL to improve the lake’s quality.  As part of the planned control measures, alum was again added to the lake at a low dose of 2.5 mg/L Al during August 1-4, 2006 to achieve short term control of TP and minimize late summer algal blooms.  Alum was applied again during April 11-14, 2007 at a high dose of 17.5 mg/L Al, based on sediment P concentration, for long-term control.

Sampling of Long Lake for the previous long-term project by Kitsap County and CILL was continued through 2010.  Historical data were compared with 2006-2010 data in the annual report on Long Lake Water Quality, February 2010.  For that report, 2010 data were integrated with 2006-2009 data to show that summer TP gradually increased, but was still below the 2006 pretreatment level, while chl remained well below pretreatment levels averaging less than 10 µg/L (Figure 1). Transparency averaged about 0.5 m greater during the last four years of monitoring than the pretreatment depth of visibility in 2006.

Scope of Work - Long Lake Integrated/Adaptive Management Plan

The following scope of work describes the specific activities that will be perform in order to enable the Kitsap County’s Long Lake Management District to meet the requirements of the Long Lake Integrated/Adaptive Lake Management Plan. Building upon the recent lake management efforts at the lake an integrated/adaptive lake management plan will be prepared and implemented. Specifically, implementation of in-lake activities that will lead to a balanced ecosystem that supports water contact recreation, sport fishery, salmon migration, ecological sustainability and aesthetic appeal. To meet these goals the lake management program will limit internal phosphorus loading to reduce excessive phytoplankton production, will control excess population of rooted aquatic plants, and eliminate, where possible, non-native plants such as Eurasian watermilfoil. The integrated management program for Long Lake includes six basic elements. Specific scope of work elements are outlined below:

Task 1 - Project Management

1.1 Project Management (PM) responsibilities shall include maintenance of project records, progress reports, and submittal of required performance items.

1.2 Efforts shall include conducting, coordinating, and scheduling project activities and assuring quality control.

Deliverables:

1. Effective administration and management of this project.

2. Maintenance of all project records.

3. Submittal of all required performance items, progress reports, invoices, and maintenance of all project records.

Schedule of Activities:

- PM activities will be carried out throughout the project from authorization to proceed in 2014 through December 2023

Budget  $80,000 (Tt $40,000 and Kitsap County $40,000)

Proposed Responsibility of Effort:

- Kitsap County would provide approximately 50% of the PM coordination and administration, through its signed PM and Department

- Tetra Tech, Inc. (Tt) would provide the other 50% of the PM by leading technical documentation, QA/QC, invoicing  and progress reports

Task 2 – Planning and Permitting

2.1 Development of a QAPP for adaptive effectiveness evaluation.

2.2 Development of a 10-year an integrated/adaptive management plan for the lake.

Deliverables:

- Necessary permit(s) applications for in-lake activities.

The Kitsap County PM will lead the permit process and maintain the permits with Tt providing the necessary technical material and permit compliance activities

- A 10-year integrated/adaptive lake management plan including the QAPP.

Tt will draft plan and QAPP.

Schedule of Activities:

- Permit activities will be carried out annually throughout the project from authorization to proceed in 2014 through December 2023

- The integrated/adaptive management plan within 90 days of formation of LMD.

Budget  $50,000 ($35,000 Tt and $15,000 Kitsap County)

Task 3 – In-lake Activities Design and Implementation

Tt will be responsible for all elements of Task 3

3.1 Design phosphorus management activities both maintenance treatments and sediment inactivation treatments.

3.2 Implementation of phosphorus management in-lake activities.

3.3 Update the IAVMP (Integrated Aquatic Vegetation Management Plan) and prepare treatment specifications for management control effort for EWM (Eurasian Watermilfoil) and Brazilian elodea as well as, for management control of specific boating lanes based.

3.4 Implement the annual aquatic plant management activities.

Deliverables:

1. Alum treatment design.

2. Update the IAVMP.

3. Implementation of in-lake phosphorus management activities.

4. Implementation of aquatic plant management activities.

Schedule of Activities:

- Design elements will be initially conducted within the first 6 months of LMD formation with on-going review and annual modifications to activities carried out through December 2023.

- The IAVMP updated within 180 days of formation of LMD with annual updates based upon data results and lake requirements.

- Implementation of phosphorus management activities as needed.

- Implementation of aquatic plant control activities as needed.

Budget  $460,000

Task 4 – Lake and Stream Monitoring

Tt will be responsible for the following elements of Task 4.

Conduct an on-going monitoring program to track phosphorus, phytoplankton production and aquatic macrophytes (visual mapping conducted twice annually) in the lake. This information shall be used to assess management progress relative to the long-term integrated/adaptive management program and be used to adjust the plan’s activities relative to the effectiveness of those activities.

Conduct water quality sampling of Long Lake at the previously established midlake station. Monthly samples will be taken at 0.5 m depth for TP, SRP, chlorophyll and profiles for dissolved oxygen, conductivity, and pH will be measured. A phytoplankton sample will also be collected. Between mid-May and mid-October addition TP and SRP samples will be taken at 2.5 m depth. Lake and Salmonberry Creek will be sampled monthly for TP and SRP. Water samples will be sent to Aquatic Research, Inc. in Seattle, on the same day as collected for filtering and analysis.

Tt will obtain stream gage data from Kitsap County Public Works Stormwater Division or the Kitsap Public Utility District web accessible stream data for continuous gages at Curley and Salmonberry Creek. Tetra Tech in coordination with CILL will install and maintain a data logger to collect lake level data.

Deliverables:

1. Limnological data collection and data management

2. Aquatic plant data collection and data management

3. Inlet and outlet surface water flow and quality data.

Schedule of Activities:

- Monitoring activities will be carried out throughout the project from authorization to proceed in 2014 through December 2023

Budget  $180,000

Task 5 – Reporting

Tt will produce all technical reports for review and approval by the Kitsap County PM.

5.1 annual assessments of in-lake activities and monitoring data will be produced in a technical memorandum format. This memorandum will also recommend activities for the next year revising the adaptive plan as dictated by the data.

5.2 Final project completion report will record data, finding and activities over the ten year LMD.

Deliverables:

1. Annual Summary Memos

2. Draft and final LMD ten year report

Schedule of Activities:

- Annual technical memorandum will be produced every December starting in 2014 through 2023.

- In December 2023 a draft and final project report will be produced.

Budget  $96,000 ($80,000 Tt and $16,000 Kitsap County)

Task 6 – Public Education

Kitsap County PM will coordinate Task 6 with Tt technical and presentation support.

6.1 One (1) public information meeting will be held each year. At these meetings, the management activities will be discussed as will water quality and aquatic plant data. A spokesperson from Tt will assist in the presentation. Public input will be taken relative to the perception of in-lake activities effectiveness and this information will be used in the updating of the annual adaptive plan.

6.2 A Public Involvement and Education Plan (PIEP) for developing and implementing the public education and outreach for the citizens of Long Lake and its watershed will be produced by Kitsap County. The plan will specify the goals and objectives of the outreach efforts to inform citizens about water quality and aquatic plant data results, and educate residents about actions they can take to reduce phosphorus entering the lake.

6.3 A High School Science Outreach Program will be developed to promote watershed and lake environmental awareness and stewardship. Kitsap County PM will coordinate with the local High School students and environmental educators at the appropriate agencies involved in the STEM field-based learning program to develop a field-based learning opportunity.

Deliverables:

1. At a minimum, one public informational meeting annually.

2. Completion and implementation of a Public Involvement and Education Plan.

3. High School Science Field-Based Learning Program

Budget  $90,000 ($60,000 Kitsap County, $10,000 Tt)

Total Budget $956,000 - Tt $805,000; Kitsap County $131,000; Reserve $38,000

Itemized Budget by Task

|  | Tetra Tech | Kitsap County | Total Cost from LMD | Kitsap County In-Kind |
| --- | --- | --- | --- | --- |
| Task 1 – Project Management | $40,000 | $40,000 | $80,000 |  |
| Task 2 – Planning and Permitting | $35,000 | $15,000 | $50,000 |  |
| Task 3 – In-Lake Activities | $460,000 | $0 | $460,000 |  |
| Task 4 – Lake and Stream Monitoring | $162,000 | $0 | $180,000 including $18,000 to Project Reserve | $50,000 (stream gaging data) |
| Task 5 - Reporting | $80,000 | $16,000 | $96,000 |  |
| Task 6 – Public Education | $10,000 | $60,000 | $90,000 including $20,000 to project reserve | $50,000 (Existing STEM Program) |
| Project Reserve |  |  | $38,000 |  |
| Total | $805,000 | $131,000 | $956,000 | ($100,000) |